BRONINGS UNIVERSITY HOSPITAL GROUP

Business Discovery Report

To: Tom Nguyen, Director of Operations    From: Lucky Ukeni, Advanced Healthcare Data Analyst    Date: 17 January 2025

1. Where we are failing

| Area | Now | NHS standard | What it means |
| --- | --- | --- | --- |
| ED 4-hour | 81.3% | 95% | 13.7 points short, and falling for five months in a row |
| RTT 18-week | 74.8% | 92% | 17.2 points short; 312 patients waiting over a year, 47 over two years |
| Theatre utilisation | 63% | 85% | 22 points short; about £180,000 a month of paid-for theatre time unused |

2. The data problem

At the last Board, the DNA rate was given as 12.4%, 9.8% and 14.1% from the same data. None is right: one was typed in last September, one formula counts the header row and cancelled appointments, and one uses a different date range. The weekly summary sheet has been wrong since October 2023, the RTT figure may date from August 2024, and the ED figure is counted by hand.

Why it matters: The Board argues about numbers instead of fixing performance, and NHS England already flags our mismatched submissions. Our national data quality score is 52 out of 100; the pass mark is 75.

What caused it: no agreed KPI definitions; manual copy-and-paste with no version control; known faults in the data feeds (shortened NHS numbers, old specialty codes, missing agency flags) that were never fixed; and no owner since the previous analyst left.

3. Financial stakes

The Trust estimates £4.2 million a year at risk: unused theatres (£180k a month), inpatient episodes not coded and therefore not paid (£51.8k a month), untracked agency spend (estimated £2.3m a year), fines of £14k per patient waiting over 52 weeks, and £380k of quality income. These items add up to more than £4.2m, so I will agree the basis with Priya before we quote a total.

4. My approach

- Phase 3 (by 31 Jan): repair the outpatient workbook, log each error and how much it moves each figure, and set one correct DNA rate.

- Phase 4 (by 7 Feb): SQL checks to find root causes, such as why our RTT count differs from the national portal's.

- Phase 5 (by 14 Feb): agree 18 KPI definitions, each with one formula and one owner.

- Phases 6–7 (by 7 Mar): Power BI and Tableau dashboards, plus an automated weekly exception report replacing manual copy-and-paste.

- Phase 8 (by 14 Mar): Board presentation built on figures you can defend.

Why this order: we cannot fix what we cannot measure.

5. The deadline

NHS England's review team arrives on Monday 24 March 2025, ten weeks from now, on a fixed date. They will test whether we understand our performance, can explain each figure, and have a credible recovery plan. If we cannot explain our own DNA rate, we fail the governance part of the review whatever our actual performance.

What you can use today: ED 4-hour and the 52- and 104-week counts, with caveats. Hold back the DNA rate and the 74.8% RTT figure until I re-check them.